## Sheet1
| Escalation | Date Opened | Tech Support | RV100 software version | Customer | SAP Service Notification | Escalation description | Engineering analysis | Status | Who Caused? | Complaint open?
1 | 77229 | 2018-08-20 | Patrick Malfi | Not known | Medical Associates of Cambridge | 302153217 | RV100 not submitting exams 302153217 | Exams got submitted. Tech support unable to get log files from customer. | Closed. | Unknown | 600491124
2 | 77248 | 2018-08-22 | Jerry Hence | 6.10.01 | Bridlewood Family Healthcare | 302154959 | RVN- Exams Stuck on Camera | (09/12/18) - Darla was able to get a hold of a Netgear manager and he reconfigured thier network. She is able to register the camera, schedule and submit a demo patient. | Closed | Customer network issue | No Complaint open
3 | 77266 | 2018-08-23 | Jerry Hence | 6.10.02 | Golden Shore Medical Group | 302155643 | RVN - Exams stuck on Camera Golden Shore | QoS settings on the server were reset to default settings instead of what they are supposed to be for the wireless client service. Friday 2018-8-24 1.37pm | Closed | WA | 600491937
4 | 77287 | 2018-08-24 | David Calabro | Not known | GMP Network | 302156191 | RVN - X cloud | QoS Setting. Exams were submitted by customer with a retry. | Resolve | WA | 600492313
5 | 77317 | 2018-08-27 | Aaron Robinson | 6.10.02 | Lodi Memorial Hospital | 302156967 | RV100-Cloud with an "X" msg | 9/12 -Jonathan Braff to set up another call with Customer | Active | Investigating | 600492729
6 | 77325 | 2018-08-28 | Jerry Hence | 6.10.01 | COPC Westerville | 302155085 | RVN - Exams stuck on camera. | 9/12 - New log files & GUID# for Eng to analyse after customer power cycled RV100. | Active | Investigating | No Complaint open
7 | N/A | 2018-08-20 | Walker Survey | Not known | Physician Care Center | 302153113 | RV100-Cloud with an "X" | Camera arrived 9/12 and is in Rob's hands for evaluation | N/A | NPF | 600490977
8 | 77487 | 2018-08-30 | Jerry Hence | 6.10.01 | Clinic Adventist Health Office Caruthers East | 302159111 | Clinic Adventist Health Office Caruthers East | 9/12 - David McClain contacted IT and had them unblock 8.8.4.4. Then get customer to retry camera. | Active | Investigating | No Complaint open
9 | 77490 | 2018-08-31 | Aaron Robinson | 6.10.02 | Jencare Neighborhood Medical Ctr | 302159429 | RV100-Cloud with an "X" msg (JenCare) | No Log files. Exams got submitted themselves during Tech Support call. | Closed | Unknown | 600494107

## Historical info before 8202018
| Escalation | Date Opened | Tech Support | RV100 software version | Customer | SAP Service Notification | Escalation description | Engineering analysis | Status | Who Caused? | Complaint open?
1 | 75865 | 2018-03-01 | Kenneth Stoutenger | 6.10.02 | Bowden Internal Medicine | 302071571 | RVN - WiFi Workflow exams Won't Submit | No root cause. Customer using USB workflow instead. | Closed | no root cause | 600455232
2 | 76696 | 2018-07-11 | Aaron Robinson | 6.00.00 | Dialysis Clinic Inc | 302133675 | RV100 - Unable to submit Exam WiFi | Customer IT issue | Closed | Customer | 600481954
3 | 76955 | 2018-07-31 | Jerry Hence | 6.10.01 | Vandage Medical Group | 302143731 | RVN - Exam stuck on camera | No engineering analysis. Exams submitted themselves and ticket closed | Closed | no root cause | No Complaint open
4 | 76455 | 2018-06-12 | David Calabro | 6.10.01 | Intermountain Cottonwood Med Clnc | 302118694 | Failed to connect to portal | Engineering recommended correct URL to use | Closed | Customer | 600474686
5 | 77197 | 2018-08-14 | Jerry Hence | 6.00.00 | Adventist Health Medical Office | 302150950 | RVN- Exams Stuck on Camera | Per Koo - camera was not able to communicate to RVN Server -but no further eng analysis. Customer's exams self-submitted and Ticket closed. | Closed | no root cause | No Complaint open